## ProjectName
Application | # | Activity | Task | Planned Hrs | Planned Start Date | Planned End Date | Actual Hrs | Actual Start Date | Actual End Date | Resource | Status | Remarks
University Admission System | 1 | Analysis | Requirement Analysis | 1 | 2017-11-28 | 2017-11-28 | 1 | 2017-11-28 | 2017-11-28 | Chitransh, Gaurav, Kireeti, Jenil, Shreyansh, Arshjeet | completed
|  |  | Preparing understanding document | 1 | 2017-11-28 | 2017-11-28 | 1 | 2017-11-28 | 2017-11-28 | Gaurav, Kireeti. | completed
|  |  | Updating QTS | 1 | 2017-11-28 | 2017-11-28 | 0.5 | 2017-11-28 | 2017-11-28 | Gaurav, Kireeti. | completed
|  |  | Understanding HLD/Class Diagram Prep | 2 | 2017-11-28 | 2017-11-28 | 2 | 2017-11-28 | 2017-11-28 | Chitransh, Gaurav, Kireeti. | completed
|  | Design | Unit Test Plan Preparation | 1 | 2017-11-29 | 2017-11-29 | 1.5 | 2017-11-29 | 2017-11-29 | Shreyansh, Jenil | completed
|  |  | LLD Preparation | 3 | 2017-11-30 | 2017-11-30 | 3 | 2017-11-30 | 2017-11-30 | Jenil | completed
|  |  | UTP Review | 0.5 | 2017-12-01 | 2017-12-01 | 0.5 | 2017-12-01 | 2017-12-01 | Gaurav | completed
|  |  | UTP Rework | 1 | 2017-11-30 | 2017-11-30 | 1 | 2017-11-30 | 2017-11-30 | Kireeti | completed
|  |  | LLD Review | 1 | 2017-11-30 | 2017-11-30 | 1 | 2017-11-30 | 2017-11-30 | Arshjeet | completed
|  | Build | Coding | 6 | 2017-12-02 | 20/10/2017 | 6 | 2017-12-02 | 2017-12-02 | Chitransh,Gaurav,Kireeti,Jenil,Shreyansh | completed
|  |  | Code Self Review | 3 | 2017-12-02 | 2017-12-02 | 3 | 2017-12-02 | 2017-12-02 | Jenil | completed
|  |  | Self Testing | 2 | 2017-12-03 | 2017-12-03 | 2 | 2017-12-03 | 2017-12-03 | Shreyansh | completed
|  |  | Rework | 3 | 2017-12-03 | 2017-12-03 | 3 | 2017-12-03 | 2017-12-03 | Kireeti | completed
|  |  | Code Peer Review | 4 | 2017-12-03 | 2017-12-03 | 4 | 2017-12-03 | 2017-12-03 | Gaurav | completed
|  |  | Peer Testing | 5 | 2017-12-04 | 2017-12-04 | 5 | 2017-12-04 | 2017-12-04 | Chitransh | completed
|  |  | Test Result review | 2 | 2017-12-04 | 2017-12-04 | 2 | 2017-12-04 | 2017-12-04 | Gaurav,Chitransh,Arshjeet,Jenil | completed
|  |  | Rework | 1 | 2017-12-04 | 2017-12-04 | 1 | 2017-12-04 | 2017-12-04 | shreyansh,Jenil | completed
|  |  | Code Integration | 2 | 2017-12-04 | 2017-12-04 | 2 | 2017-12-04 | 2017-12-04 | Arshjeet | completed
|  |  | Integration Testing | 1 | 2017-12-05 | 2017-12-05 | 1 | 2017-12-05 | 2017-12-05 | Chitransh | completed
|  |  | Rework | 1 | 2017-12-05 | 2017-12-05 | 1 | 2017-12-05 | 2017-12-05 | Jenil | completed
|  |  | Test Result review | 1 | 2017-12-05 | 2017-12-05 | 1 | 2017-12-05 | 2017-12-05 | Gaurav, Kireeti, Jenil | completed
|  |  | Total Planned Hrs : |  |  | Total Actual Hrs: | 41.5